## Directions_Definitions
Directions
1. Create a copy of the template tab
2. Rename the tab to match the drop down for item
3. Fill in as much as possible--Be as specific as possible for mitigation items--include numbers, spacing, etc
4. Fill out Coverpage with a brief description
5. Save as Site_Mitigation tracker
Item | What is the thing.
Resident Impact | What is the impact of turing this back on for residents? High--Great impact on residents wellbeing, low-little to no impact on wellbeing
Decription Pre-COVID | Brief description of what it was before COVID changes H
Risk Level if put back as Pre-COVID-19 | Based upon Pre-COVID description what would the risk level be if NO mitigation efforts were put in place
Risk Mitigation Measures | Brief overview of what needs to be put in place to mitigate the risk if turned back on
Estimated costs | what the estimated costs in $ for both staff time and materials
Risk if put in place mitigation strategies | If mitigation measures are put in place what is the risk level
Risk Levels | High | Activity almost guarantees infection based upon CDC quidelines
Med
| Low | activity has a minimal risk to residents based upon known CDC quidelines

## timeline
Community Name
Re-Opening Planning Timeline / Phasing
Start Date:
Activity | Owner | Status | Start | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26
REOPENING PHASE I (First) |  |  | 2020-05-11 | bar: 2020-05-11 to 2020-10-26
List item | Name | On Track | 2020-05-11 | bar: 2020-05-11 to 2020-10-26
List item | Name | On Track | 2020-05-18 | bar: 2020-05-18 to 2020-10-26
List item | Name | On Track | 2020-05-25 | bar: 2020-05-25 to 2020-10-26
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
REOPENING PHASE II (Next) |  |  | 2020-07-01 | bar: 2020-05-11 to 2020-10-26
List item |  | On Track | 2020-07-01 | bar: 2020-07-06 to 2020-10-26
List item |  | On Track | 2020-07-15 | bar: 2020-07-20 to 2020-10-26
List item |  | On Track | 2020-08-15 | bar: 2020-08-17 to 2020-10-26
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
REOPENING PHASE III (Later) |  |  | 2020-09-01 | bar: 2020-05-11 to 2020-10-26
List item |  | On Track | 2020-09-15 | bar: 2020-09-21 to 2020-10-26
List item |  | On Track | 2020-09-15 | bar: 2020-09-21 to 2020-10-26
List item |  | On Track | 2020-09-30 | bar: 2020-10-05 to 2020-10-26
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
|  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X

## summary
Item | List the item
Decription Pre-COVID | Brief description of what it was before COVID changes
Pre COVID RISK | Based upon Pre-COVID description what would the risk level be if NO mitigation efforts were put in place
Risk Mitigation Measures-Brief | Brief overview of what needs to be put in place to mitigate the risk if turned back on
Post COIVD Risk | If mitigation measures are put in place what is the risk level
Item (Drop Down) | Description pre-COVID | Pre COVID Risk | Risk Mitigation Measures-Brief | Post COVID Risk
Move out | Multiple movers/family members, occurs anytime | Med | Maintenance helps, limit days to early Sat morning | Low
Move in |  | High |  | Med
Turn over
Laundry | multiple residents/aids at potential at same time |  | schedule shifts? Clean every 3 hours
Mail Delivery | residents come at same time to collect/gather in great rom
Visitors | all day everyday |  | Limit one per resident per week
Fitness Center | tight space/lots of residents |  | schedule for all- clean after every use.
Opening of community rooms | multiple residents in small space |  | limit amount of people at one time.
Walks in community | lot of people around at same time |  | wear mask, clean hall reg, schedule
Bus Trips- Groccery Store
Bus Trips- Community locations
Movie Nights
Medical Practice
Programs

## blank template
Date
Item
Resident impact
Description of work Pre-Covid-19
Risk Level if put back as Pre-Covid-19
Mitigation strategies
Estimated Costs ($)
| Staff | 0
| Material | 0
| Total | 0
Risk Level utilizing mitigation strategies

## sample_Move-Outs
Date
Item | Move out
Resident impact
Description of work Pre-Covid-19
Resident/Family member turns in notice. Unknown number of family comes into building and packs up resident. Movers come into building and move out resident. Maintenance deals with multiple interactions around trash, extra furniture
Risk Level if put back as Pre-Covid-19 |  |  | Med
Mitigation strategies
One family member is allowed in to pack
Single moving company -screened and utilizing rear elevator
Maintenance assists by moving items down to truck
Trash is removed by maintenance
family relinquish contents of unit to organization to discard of for a fee
Estimated Costs ($)
| Staff | 0
| Material | 0
| Total | 0
Risk Level utilizing mitigation strategies |  |  | Low

## sample_Move Ins
Date
Item | Move in
Resident impact |  | Low
Description of work Pre-Covid-19
Movers and/or family bring resident into the building. It occurs on any given day at any given time. Followed up with Cable/Telephone install, mutiple trips in/out and increase in trash due to moving.
Risk Level if put back as Pre-Covid-19 |  |  | High
Mitigation strategies
Limit to a certain hours on a certain day
Screen movers
Limit family interaction down to one member
Immediately isolate x 14 days
Coordinate the removal of boxes and wrapping with maintenance for pickup from apartment
Estimated Costs ($)
| Staff | 0
| Material | 0
| Total | 0
Risk Level utilizing mitigation strategies |  |  | Med

## Drop Down lists
| Risk | Residential Impact | Item
| Low | Low | Laundry
| Med | Med | Mail Delivery
| High | High | Bus Trips- Groccery Store
Bus Trips- Community locations
Opening of community rooms
Walks in community
| Status |  | Dining- Delivery
Dining-Communal
In Progress
| Completed |  | Community Meetings
| Cancelled |  | Movie Nights
| Future task |  | Resident Council Meeting (in person)
Visitors
Programs
List 1
List 2
Priority | Readiness |  | List 3
High |  |  | List 4
Medium | On Track |  | Move in
Low | Attention |  | Move out
None | At Risk |  | Turn over
| Complete |  | House Keeping
Trashrooms
Medical Practice
Therapy House Calls
Fitness Center
non-essential private aides